## Sheet1
| Project Name: | Solar Energy Analytics
| Start Date: | 2026-04-02
| Current Date: | 2026-05-17
| Weeks In-Progress: | 7
[6 empty] | 2026-04-02 | 2026-04-09 | 2026-04-16 | 2026-04-23
Task | Project Lead | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4
Planning Stage |  |  |  |  | 91.67%
1.Business Context Research & KPI Definition | Team | 2026-04-02 | 2026-04-09 | 7 | 0%
1.1 Global Solar Market Overview | Kirolos | 2026-04-02 | 2026-04-03 | 1 | 100%
1.2 Egyptian Solar Energy Landscape | Kirolos | 2026-04-03 | 2026-04-04 | 1 | 100%
1.3 Competitive & Technical Landscape | Mohamed | 2026-04-04 | 2026-04-05 | 1 | 100%
1.4 Industry Dynamics | Mohamed | 2026-04-05 | 2026-04-06 | 1 | 100%
1.5 Risks, Challenges & Mitigation | Hassan | 2026-04-06 | 2026-04-07 | 1 | 100%
1.6 Key Performance Indicators (KPIs) | Aml | 2026-04-07 | 2026-04-08 | 1 | 100%
Reviewing and final file | Hassan | 2026-04-08 | 2026-04-09 | 1 | 100%
2.Data Integration and preparation of "Single Source Of Truth" | Kirolos | 2026-04-02 | 2026-04-04 | 2 | 100%
3.Feature Selection & Analysis Strategy | Mohamed | 2026-04-04 | 2026-04-09 | 5 | 100%
4.Model Architecture & Train/Test Split | Hassan | 2026-04-09 | 2026-04-16 | 7 | 100%
5.Dashboard UI/UX Design & Metrics | Aml | 2026-04-09 | 2026-04-16 | 7 | 100%
Execution Stage |  |  |  |  | 100%
SQL Data Join (Weather + Production | Kirolos | 2026-04-09 | 2026-04-11 | 2 | 100%
Exploratory Data Analysis & Heatmaps | Mohamed | 2026-04-12 | 2026-04-15 | 3 | 100%
Training AI Engine | Hassan | 2026-04-16 | 2026-04-20 | 4 | 100%
Power BI Dashboard Development | Aml | 2026-04-21 | 2026-04-23 | 2 | 100%
Report Writing & Storytelling Compilation | Aml | 2026-04-24 | 2026-04-25 | 1 | 100%
Review Stage |  |  |  |  | 100%
Data Integrity Audit | Team | 2026-04-25 | 2026-04-26 | 1 | 100%
Outlier Cleaning & Correlation Validation | kirolos & Mohamed | 2026-04-26 | 2026-04-27 | 1 | 100%
AI Performance Audit | Hassan | 2026-04-27 | 2026-04-28 | 1 | 100%
Dashboard Integration & Value Testing | Aml | 2026-04-28 | 2026-04-29 | 1 | 100%
Final Presentation & Delivery | Team | 2026-04-29 | 2026-04-30 | 1 | 100%